## Time Frame
Volive Solutions LLC
Project Name : Engineering Works | [6 empty] | Project Start Date : 21/06/2018
Client Name : | [6 empty] | Project End Date : 04/08/2018 |  | (35 WORKING DAYS)
Platform : iOS,Android | [6 empty] | Team Lead : (Naresh)
Sr.no | Assigned Person(iOS) | Assigned Person(Android) | Module Name(User) | Module Name(Service Provider) | Implementation | Design Status(Y/N) | Service Dependency | Services Status Y/N | Start Date | End Date | Demo Date | Status
1 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Sign up service functionality and otp verification | Sign up service functionality and otp verification | Dynamic | N | y | y | 2018-06-21 | 2018-06-23
2 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Sign in service & forgot password functionality | Sign in service & forgot password functionality | Dynamic | N | y | y | 2018-06-24 | 2018-06-25
3 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Home service functionality | Home service functionality | Dynamic | N | y | y | 2018-06-26 | 2018-07-30
4 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | My Requests service functionality | My Requests service functionality | Dynamic | N | y | y | 2018-07-02 | 2018-07-04
5 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Completed orders service | Completed orders service | Dynamic | N | y | y | 2018-07-05 | 2018-07-07
6 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | For UI changes | For UI changes | Dynamic | N | y | y | 2018-07-07 | 2018-07-08
7 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Notifications Functionality | Notifications Functionality | Dynamic | N | y | y | 2018-07-09 | 2018-07-12
8 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Address Functionality | Address Functionality | Dynamic | N | y | y | 2018-07-13 | 2018-07-16
9 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Single visit and packages functionality | Single visit and packages functionality | Dynamic | N | y | y | 2018-07-17 | 2018-07-21
10 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Request details screen | Request details screen | Dynamic | N | y | y | 2018-07-23 | 2018-07-24
11 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Order details functionality | Order details functionality | Dynamic | N | y | y | 2018-07-25 | 2018-07-25
12 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Payment functionality | Payment functionality | Dynamic | N | y | y | 2018-07-26 | 2018-07-26
13 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Thank you screen functionality | Thank you screen functionality | Dynamic | N | y | y | 2018-07-27 | 2018-07-27
14 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Tracking Order Screen | Tracking Order Screen | Dynamic | N | y | y | 2018-07-30 | 2018-07-30
15 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Single visit details | Single visit details | Dynamic | N | y | N | 2018-07-31 | 2018-07-31
16 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Package Details functionality | Package Details functionality | Dynamic | N | y | N | 2018-08-01 | 2018-08-01
17 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Completed Order details and check pdf | Completed Order details and check pdf | Dynamic | N | y | N | 2018-08-02 | 2018-08-02
18 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | My Account | My Account | Dynamic | Y | y | N | 2018-08-03 | 2018-08-03
19 | Sailaja/Radha | Vineeth/Lakshmi/Khaja | Testing app functionality | Testing app functionality | Dynamic | N | y | N | 2018-08-04 | 2018-08-04
Team Size : 1
Web Development

## List Of Services
List Of Services
Registration API
Login API
Home Screen API With Total Claimed & N.of.Points & Gifts
Products API
Claimed API
About us,Privacy Policy,Contact Us API
Settings API
Shopkeeper's API
Shopkeeper's Search Bar API
Forgot Password API
QR Scan API